## 080126
Issue Summary | In CMMS/ SE | Status
IT Division shall coordinate with the Internet Service Providers (ISP) to ensure the smooth functioning of Census apps prior to the commencement of the actual HLO Phase. This will help avoid any operational disruptions for enumerators and supervisors during fieldwork. | CMMS | N/A
Name of the Charge Officer shall be clearly mentioned in the Appointment Letter of E&S. | CMMS | Closed
End time of training shall not be provided in Appointment Order of the E&S | CMMS | Closed
A standard data format shall be uniformly followed across the portal to avoid inconsistencies between bulk upload and single-entry modules on the CMMS portal. | CMMS | Closed
One enumerator will be allotted HLBs under 1 supervisor only. It may be explored if software may be designed in such a way without much difficulty that one enumerator may be allotted to more than one supervisor under exceptional circumstances. | CMMS | Under Discussion
The maximum permissible size of a training batch shall be restricted to 50 trainees for E&S. In cases where the number of trainees exceeds 50, two separate batches shall be formed. | CMMS | Closed
It shall be clearly stated in the Instruction manual or Circular that Charge Officers must be sensitized to ensure that while carving HLBs on the HLBC Web Map application, the resulting HLBs do not cut across Revenue Village mandatorily and preferably also Panchayat boundaries. | CMMS | N/A
The drop-down menu under Remarks Column of Village Register shall be revised to include the following: Forest Village Reserve Forest Uninhabited Submerged Census Town Others In case Others is selected, an editable text field should be enabled to allow the user to enter specific remarks. There should be provision to leave as blank also. | CMMS | Closed
Census Division to review and finalise format for VR/TR and CR. | CMMS | N/A
It has been decided as per discussion in the DCO Conference and internal discussion that whenever there is no change in jurisdiction of wards, 2011 ward population may be taken for comparison purpose, as mentioned in Business Requirement Document and in the format for information collection from Charge Offices based on JC Portal. | CMMS | N/A
It has been decided as per discussion in the DCO Conference that the name of districts and sub-districts may be kept as it is in town and urban charge register. Whenever there is multiple sub-district/district in a town, this field will be kept blank. | CMMS | Closed
No of reports to be made available in CMMS to be finalised. Only necessary reports which are independent in nature to be provisioned. | CMMS | Under Discussion
Progress reports to be available in real time. | CMMS | Will be done in during Production
Email issues to be taken up with NIC urgently. | CMMS | N/A
Separate framework to be provided for Practice and Training. | CMMS | Closed
The default value for number of days training attended by E&S should be 3. The CO may update as per actual attendance. In the Attendance update part of Training Module one certification from Charge Officer is required to the effect that “I certify that all E&S have attended training as shown above”. | CMMS | On-going
“Deactivated” should be used for users instead of “Inactive”. | CMMS | Closed
The roles of E&S will not be available for reversal after user creation. | CMMS | N/A
Testing Plan with guidelines for testing of all Digital Tools to be prepared and shared with DCOs asap. | CMMS | N/A
It was finalized that capturing location of the SE respondent is to be done on the SE portal itself. To ensure accuracy, the integrated map API must be robust and optimally configured. | SE | On-going
It was also decided to drop DIGIPIN feature due to its unstable database. Instead, the latitude and longitude of the location marked by the SE respondent will be recorded. | SE | On-going
Language selection for SE will be prompted and allowed only Once. | SE | Closed
Selection of State and District shall be made mandatory for SE respondents when searching for their location. | SE | Closed
SE progress status at State, District level to be available to DCO State and District Logins. | SE | On-going
Editing of information submitted through Self-Enumeration shall be restricted to a total of three attempts—once before first submission and two subsequent edits. | SE | Closed
A 100-meter buffer distance shall be maintained for capturing the SE ID in both rural and urban areas. | SE | N/A
Session Management to be properly maintained, with automatic logout set to occur 15 minutes after the last edit. | SE | Closed
Re-login for SE will be validated through the registered mobile number only. | SE | Closed
Awareness for public is Necessary for Cooperation in Self Enumeration | SE | N/A
Base maps provided in SE portal to select the location of SE houses lacked clarity. Search location not accurate, DIGIPIN and locality searches failed to point correctly. Difficult for the normal public to locate their home in map. | SE | On-going
Enumerators reported that they received “invalid” message when SE ID was entered for matching. SE Ids not reflected in the HLB even though correct location etc. also reported. | SE | On-going
Self-Enumeration topics may be sequenced before the HLO App topics in training. | SE | N/A
Along with the display of SE ID after submission of SE details, a message also may be displayed stating that – “You are requested to share this reference ID with the enumerator to complete your HLO. If not, a fresh enumeration may be required” | SE | Closed
Ward No. filled during Self Enumeration was not displayed in preview. It was shown as NA. | SE | On-going
In Preview of SE, house number was displayed against locality name | SE | Closed
While doing Self Enumeration in portal, automatic logout was happening. | SE | Closed
Many households deleted the SMS regarding generated SE ID before enumerators visit. Publicity will be done, however during Census same can be retrieved through Know your reference ID module in SE portal. Also, if email id is provided, the SE Id is being sent there also. | SE | N/A
During Self-Enumeration , if the user tries to edit any previously entered data, the system prompts for another mobile number to receive a fresh OTP. This prevents the user from continuing with the same mobile number used originally. | SE | On-going
After the deadline (7th Nov), the system correctly displays a message: “You cannot do after 7 Nov.” and disables the “Edit/Change” button on the profile page. However, if the user presses the mobile browser’s “Back” button, the browser loads a cached editable version of the page, allowing the user to bypass the restriction and modify SE ID details even after the deadline. | SE | Closed
Facility to view Progress Report of Self Enumeration District/Charge wise in CMMS portal should be provided at State Level, District Level, DCO Level. | SE | On-going
In the SE Portal, typing in the regional language is difficult. | SE | Closed
During Self-Enumeration in the Telugu language, users face difficulties entering the name of the head of the household. There is no option to switch languages after selection. | SE | On-going
Explainer video on SE process and procedures may be provided in the Portal | SE | N/A