## Sheet1
S. No. | Vulnerability Name | Risk Level | Status | Details | Date
1 | OTP Bypass through response manipulation | High | on going
2 | Improper Session Termination | High | ongoing | No backend API For Logout , handled from the frontend itself. | 2026-02-27
3 | Account takeover via forgot password | High | close | The forgot password reset is being sent to the registered email | 2026-02-27
4 | Unwanted HTTP methods | MEDIUM | close | Only GET , POST Methods used | 2026-02-26
5 | OTP Bruteforce Attack | MEDIUM | Open | OTP Getting to the registered email but no provision for the number of attempts | 2026-02-27
6 | Concurrent sessions | MEDIUM | Open | same account logged in multple places | 2026-02-26
7 | Missing Authentication on Sensitive LogoutAPI | MEDIUM | close | No backend API For Logout , handled from the frontend itself. | 2026-02-25
8 | Improper CAPTCHA Implementation | MEDIUM | close | captcha working fine from the backend service ( Auth-service) | 2026-02-25
9 | Missing Custom Error Pages | Low | close | custom error page for 404 present in frontend end ( PageNotFound.js) | 2026-02-25
10 | CORS Misconfiguration | Low | close | CORS configuration is done for the local system and the IP | 2026-02-26
11 | Improper Input Validation | Low | open | In some forms the space is not getting passed | 2026-02-25
12 | Possible Brute force through Race Condition | Low | ongoing
13 | Favicon disclosure | Info | close | no icon of the technology used is present in the project | 2026-02-25